## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Rare Bookstore
| Project | Bookstore Management System
| Product Owner | Daniel Rhoads
| Scrum Master | Pablo Gomez
| Development Team | Team RISE
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Inventory Management System | As a bookstore employee, I want to digitally catalog rare books so that inventory is accurate, searchable, and easy to manage. Security Consideration: Access to inventory modification must require authenticated login with role-based permissions. | Users can add, edit, and delete book records. Each book record includes title, author, edition, condition, price, and unique ID. System prevents duplicate unique IDs. Inventory updates reflect in real time. Only authorized roles can modify records. | 1 | 1 | Alyssa Brown
2 | Accounting & Financial Tracking | As the store owner, I want automated financial tracking so that I can monitor revenue, expenses, and profitability in real time. Security Consideration: Financial data must be encrypted and restricted to authorized personnel. | Sales transactions automatically update financial reports. System generates daily, weekly, and monthly revenue reports. Expense entries can be recorded and categorized. Financial dashboard displays profit/loss summaries. Access limited to management roles. | 1 | 2 | Alyssa Brown
3 | Supplier Ordering System | As a purchasing manager, I want to manage supplier orders digitally so that restocking is efficient and traceable. Security Consideration: Supplier data must be protected from unauthorized access or modification. | Users can create and track supplier orders. System logs order date, supplier name, items, and status. Low-stock alerts trigger reorder notifications. Order history is searchable. Only authorized users can approve purchase orders. | 2 | 2 | Gustavo Rosas
4 | Customer Sales & Checkout | As a sales associate, I want a digital checkout system so that customer purchases are processed quickly and accurately. Security Consideration: Payment information must comply with data protection standards and not store sensitive payment data improperly. | Users can search inventory during checkout. Sales transactions automatically deduct stock. System generates digital receipts. Sales are logged for reporting purposes. Payment data is processed securely. | 1 | 1 | Daniel Rhoads
5 | Reporting & Analytics Dashboard | As the store owner, I want real-time reporting so that I can make informed business decisions. Security Consideration: Reports must only be accessible to authorized roles. | Dashboard displays inventory levels. Dashboard displays sales trends. Reports can be exported (PDF/CSV). Data refreshes automatically. Role-based access enforced. | 2 | 2 | Daniel Rhoads
6 | User Authentication & Role Management (Security) | As a system administrator, I want user authentication and role-based access control so that sensitive data is protected. Security Consideration: Passwords must be encrypted and multi-factor authentication should be supported. | Users must log in with secure credentials. Passwords are encrypted in storage. Roles include Admin, Manager, Sales Associate. Permissions restrict access to sensitive modules. Account lockout after multiple failed attempts. | 1 | 1 | Alyssa Brown
7 | Data Migration & System Deployment | As the bookstore owner, I want existing paper records digitized so that historical data is preserved. Security Consideration: Data migration must ensure data integrity and prevent data loss. | Existing inventory records are digitized. Data accuracy is verified after migration. Backup is created before migration. System is deployed and accessible to staff. Final stakeholder approval obtained. | 2 | 2 | Gustavo Rosas

## Sprint 1
Sprint #Tracking Sheet
Project
Sprint #
Start date
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #Tracking Sheet
Project
Sprint #
Start date
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0