## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Project | Rare Book Inventory & Sales Ecosystem (RISE)
| Detailed Oriented Tester | Lyiondra Bradley
| Logic Architect (Backend Developer) | Midori (Alyssa Brown)
| Scrum Master | Pablo Gomez
| UI/UX (Frontend Developer) | Daniel Rhoads
| Business Analyst | Gustavo Rosas
Story ID | Title |  | Acceptance Criteria | Priority # | Sprint # | Responsibility
Story SO-01 | Project Infrastructure | As a Team, we want a centralized repository and baseline environment so that we can collaborate on documentation and technical design without version conflicts. | 1. GitHub Repository initialized with README and folder structure. | 1 | 0 | Daniel Rhoads
Story SO-02 | UI Design System | As a UX/UI Lead, I want to establish global CSS variables and a functional prototype to prove technical feasibility. | 1. CSS variables for Midnight Blue/Emerald Green defined. 2. Prototype validates localStorage persistence. | 1 | 0 | Daniel Rhoads
Story SO-03 | Test Strategy | As a Tester, I want to define a comprehensive test strategy to ensure high software quality in the implementation phase. | 1. Testing goals documented in repo. 2. Initial test cases mapped for CRUD and Sales. | 1 | 0 | Lyiondra Bradley
[5 empty] | 2 | Gustavo / Daniel

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | RISE (Rare Book Inventory & Sales Ecosystem)
|  | Sprint # |  | 1
|  | Start date |  | 2026-02-24
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09
T1-01 | Story-01 | Design HTML/Bootstrap layout for Inventory Table | Daniel Rhoads | 4
T1-02 | Story-01 | Script JavaScript logic for 'Add Book and Delete' | Midori | 8
T1-03 | Story-01 | Implement LocalStorage persistance for books | Midori | 4
T1-04 | Story-03 | Create Login Form and validation logic | Daniel /Midori | 6
T1-05 | Story-04 | Creae RegEx Patterns for ISBN and Price validation | Lyiondra | 4
T1-06 | Story-02 | Build POS Checkout Interface and subtotal logic | Midori | 10
|  | Remaining units (actual) |  | 80 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[10 empty] | 0 | 36 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Rare Book Inventory & Sales Ecosystem (RISE)
|  | Sprint # |  | 2
Start date
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
T2-01 | Story-05 | Design Kanban board UI for procurement | Gustavo/Daniel | 6
T2-02 | Story-05 | Implement status-tagging logic (Ordered/Shipped) | Midori | 6
T2-03 | Story-06 | Script 15 minute inactivity timer and redirect | Midori | 4
T2-04 | Story-06 | Test session timeout across different browsers | Lyiondra
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 16 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0